## README
COMPSYS704 Project 1 — Master Interface Workbook
Source | docs/INTERFACE_FREEZE_V1.md
M3 source contract | COMPSYS704_M3_GP_IP_Integration_Interface_Contract_V2_1.docx
Current GP / Visualisation status | FROZEN V1
M3-facing V2.1 contract | FROZEN — effective 28 August 2026
M1 FT implementation | PARTIAL — inputs/state/mapping implemented; safe-stop ACK and resume decision not emitted without evidence/schema
External port blockers | M1, M3 and M4 production source/XML is present and structurally validated. Remaining external blockers are M2 Loader/Conveyor/Labeller/Unloader/Transfer Adapter endpoints and the full M2-to-M4 downstream hand-off.
Purpose | Current master view separating contract status, implementation status and owner/blocker
Contract set checked | M2 V1.0 + M3 V2.1 + M4 V1.2 rechecked 2 September 2026. M1/M3/M4 production mappings are registered; M4 two-size implementation and tests pass; unresolved receiver warnings are M2-owned.
Version / Integration State
Boundary | Contract Status | Implementation Status
Existing GP / POS / Visualisation | FROZEN V1 | Implemented at M1, M3 and M4 ends; M2 peer Controllers remain external
Explicit M3-facing V2.1 boundaries | FROZEN | M3 production Rotary/Lid/Fault Supervisor source, XML and self-tests are present; M2 Transfer peer remains pending
M2-owned receiver numbers | M2 ASSIGNED — 28 August 2026 | Conveyor 11009; Labeller 11013; Transfer Adapter 13002; DigitalTwinCD 14002. No conflict with M4 11011/11012 or M3 13003.
Earlier M3 V1 FT proposal | SUPERSEDED for explicit V2.1 boundaries | Retained only as migration/history in the Markdown
M2 Digital Twin IP | MILESTONE 1 CONCEPTUAL INTERFACE | Bottle/workpiece and resource-twin update/query boundaries documented; implementation and final transport schema pending.
Key Rules
1 | Receiver owner assigns the port; do not invent an M2 port.
2 | Status polling is read-only and must never start, acknowledge, reset or advance physical work.
3 | FaultSupervisorCD and CoordinatorCD never directly operate machine actuators or write Plant state.
4 | FT_FAULT_ALERT is observational; FT_RECOVERY_READY never auto-resumes production.
5 | FT_SAFE_STOP_ACK requires independent physical safe-stop evidence; no evidence means no ACK.
6 | M1 alone owns final RESUME/HOLD; exact M1 FT payload field order is still unresolved.
7 | P1/P6 are machine/Plant hand-offs and must not be added to CoordinatorCD.
8 | Advanced Visualisation remains display-only; no Label telemetry is invented.
9 | Digital Twin updates and snapshots are informational; local Controllers and Plant sensors remain authoritative for actuation.
M2 source contract | COMPSYS704_M2_GP_IP_Integration_Interface_Contract_V1_0.docx
M4 source contract | COMPSYS704_M4_GP_IP_Integration_Interface_Contract_V1_2.docx
M4 V1.2 Sync Rules
10 | Full BottleContext is bottleId¦sizeCode¦capacityMl¦geometryProfileId¦packagingProfileId; only S¦200¦GEOM_S¦PACK_S and L¦500¦GEOM_L¦PACK_L are valid.
11 | Current M1 OrderV1 validation confirms each dispatched Integer A/B pair is within 0..100 and sums to 100; M4 validates local inputs and the measured-A complement.
12 | BOTTLE_DONE remains exclusively M2 Bottle Unloader-owned. Each logical pure-signal event uses one bounded PRESENT window followed by an ABSENT gap; M1 counts only its rising edge.
13 | ROTARY_BOTTLE_CONTEXT, BOTTLE_AT_FILL and BOTTLE_AT_CAP are implemented at the M4 and M3 endpoints using the unchanged full BottleContext; they are machine-to-machine signals, not M1 Coordinator signals.
14 | M4 target volumes are targetAMl = capacityMl × ratioA / 100 and targetBMl = capacityMl × ratioB / 100. For supported capacities and Integer ratios, results must be integral mL; no rounding is permitted.
15 | bottleId is a non-empty, case-sensitive ASCII token with no pipe, CR, LF, or leading/trailing whitespace; preserve it byte-for-byte across Recognition, Registry, M2, M3, and M4.

## Interfaces
Category | Sender | Receiver | Signal | Type / Transport | Meaning / Purpose | IP | Receiver Port | Contract Status | Implementation / Verification | Requirement
GP / POS | POSCD | CoordinatorCD | ORDER | String | Purchase-order payload. POS may transmit the same validated payload as up to three bounded PRESENT transport copies; Coordinator accepts one copy and does not restart an active or already-completed order ID. | 127.0.0.1 | 11001 | FROZEN V1 | Implemented at both ends
GP / POS | CoordinatorCD | POSCD | ORDER_COMPLETE | String | Completion payload. Coordinator may transmit the same payload as up to three bounded PRESENT transport copies; POS de-duplicates repeats and ignores stale/non-active completions. | 127.0.0.1 | 11000 | FROZEN V1 | Implemented at both ends
Machine Controller | CoordinatorCD | BottleLoaderControllerCD | START_ORDER | Integer | Bottle quantity for the current product batch | 127.0.0.1 | 11002 | FROZEN V1 | M1 implemented; peer not in repository
Machine Controller | CoordinatorCD | BottleLoaderControllerCD | LOADER_STATUS_REQUEST | pure signal | Read-only request for current Loader status | 127.0.0.1 | 11002 | FROZEN V1 | M1 implemented; peer not in repository | Polling only
Machine Controller | BottleLoaderControllerCD | CoordinatorCD | LOADER_STATUS | Integer | Latest Loader status | 127.0.0.1 | 11001 | FROZEN V1 | M1 receiver implemented; peer not in repository
Machine Controller | CoordinatorCD | ConveyorControllerCD | CONVEYOR_STATUS_REQUEST | pure signal | Read-only request for current Conveyor status | 127.0.0.1 | 11009 | FROZEN V2.1; M2 PORT ASSIGNED | M1 production XML targets ConveyorControllerCD:11009; M2 peer SystemJ/XML implementation remains unavailable. | Polling only
Machine Controller | ConveyorControllerCD | CoordinatorCD | CONVEYOR_STATUS | Integer | Latest Conveyor status | 127.0.0.1 | 11001 | FROZEN V2.1 | M2 conceptual sender defined; SystemJ/XML implementation pending
Machine Controller | CoordinatorCD | RotaryTableControllerCD | ROTARY_STATUS_REQUEST | pure signal | Read-only request for current Rotary status | 127.0.0.1 | 11003 | FROZEN V2.1; M1 MAPPING ALIGNED | M1 sender and M3 RotaryTableControllerCD:11003 receiver are implemented and aligned. | Polling only
Machine Controller | RotaryTableControllerCD | CoordinatorCD | ROTARY_STATUS | Integer | Latest Rotary status | 127.0.0.1 | 11001 | FROZEN V2.1; M1 MAPPING ALIGNED | M3 sender and M1 CoordinatorCD:11001 receiver are implemented.
Machine Controller | CoordinatorCD | FillerAControllerCD | FILL_A_RATIO | Integer | Liquid A percentage, 0-100; M1 confirms the dispatched A/B pair sums to 100 before dispatch | 127.0.0.1 | 11004 | FROZEN V1; M4 V1.2 TRUST BOUNDARY | Implemented at M1 sender and M4 FillerAControllerCD receiver; M1 validates the 0..100 complementary recipe pair and M4 validates its local input. | Recipe input only; never an actuator command
Machine Controller | CoordinatorCD | FillerAControllerCD | FILLER_A_STATUS_REQUEST | pure signal | Read-only request for current Filler A status | 127.0.0.1 | 11004 | FROZEN V1 | Implemented at M1 sender and M4 receiver; polling is read-only. | Polling only
Machine Controller | FillerAControllerCD | CoordinatorCD | FILLER_A_STATUS | Integer | Latest Filler A status | 127.0.0.1 | 11001 | FROZEN V1 | Implemented at M4 sender and M1 receiver.
Machine Controller | CoordinatorCD | FillerBControllerCD | FILL_B_RATIO | Integer | Liquid B percentage, 0-100; M1 confirms the dispatched A/B pair sums to 100 before dispatch | 127.0.0.1 | 11005 | FROZEN V1; M4 V1.2 TRUST BOUNDARY | Implemented at M1 sender and M4 FillerBControllerCD receiver; measured-A complement is checked before B dosing. | Recipe input only; never an actuator command
Machine Controller | CoordinatorCD | FillerBControllerCD | FILLER_B_STATUS_REQUEST | pure signal | Read-only request for current Filler B status | 127.0.0.1 | 11005 | FROZEN V1 | Implemented at M1 sender and M4 receiver; polling is read-only. | Polling only
Machine Controller | FillerBControllerCD | CoordinatorCD | FILLER_B_STATUS | Integer | Latest Filler B status | 127.0.0.1 | 11001 | FROZEN V1 | Implemented at M4 sender and M1 receiver.
Machine Controller | CoordinatorCD | LidLoaderControllerCD | LID_STATUS_REQUEST | pure signal | Read-only request for current Lid status | 127.0.0.1 | 11006 | FROZEN V2.1 | Implemented at M1 sender and M3 receiver; polling is read-only. | Polling only
Machine Controller | LidLoaderControllerCD | CoordinatorCD | LID_STATUS | Integer | Latest Lid status | 127.0.0.1 | 11001 | FROZEN V2.1 | Implemented at M3 sender and M1 receiver.
Machine Controller | CoordinatorCD | CapperControllerCD | CAPPER_STATUS_REQUEST | pure signal | Read-only request for current Capper status | 127.0.0.1 | 11007 | FROZEN V1 | Implemented at M1 sender and M4 receiver; polling is read-only. | Polling only
Machine Controller | CapperControllerCD | CoordinatorCD | CAPPER_STATUS | Integer | Latest Capper status | 127.0.0.1 | 11001 | FROZEN V1 | Implemented at M4 sender and M1 receiver.
Machine Controller | CoordinatorCD | BottleUnloaderControllerCD | UNLOADER_STATUS_REQUEST | pure signal | Read-only request for current Unloader status | 127.0.0.1 | 11010 | FROZEN V1 | M1 implemented; peer not in repository | Polling only
Machine Controller | BottleUnloaderControllerCD | CoordinatorCD | UNLOADER_STATUS | Integer | Latest Unloader status | 127.0.0.1 | 11001 | FROZEN V1 | M1 receiver implemented; peer not in repository
Machine Controller | BottleUnloaderControllerCD | CoordinatorCD | BOTTLE_DONE | pure signal | Exactly one logical finished-bottle event after verified removal. Hold the pure signal PRESENT for one bounded observable window, then provide an ABSENT gap before the next bottle event. | 127.0.0.1 | 11001 | FROZEN V1 | M1 edge-latched receiver and integration Mock implemented; real M2 peer source/XML unavailable. | One bounded PRESENT window per bottle; no retry copies; at least one ABSENT reaction between bottles.
Advanced Visualisation | CoordinatorCD | ABSVisualisationPlantCD | VIZ_LOADER_STATUS | Integer | Display latest Loader status | 127.0.0.1 | 11008 | FROZEN V1 | Implemented at both M1 ends | Display only
Advanced Visualisation | CoordinatorCD | ABSVisualisationPlantCD | VIZ_CONVEYOR_STATUS | Integer | Display latest Conveyor status | 127.0.0.1 | 11008 | FROZEN V1 | Implemented at both M1 ends | Display only
Advanced Visualisation | CoordinatorCD | ABSVisualisationPlantCD | VIZ_ROTARY_STATUS | Integer | Display latest Rotary status | 127.0.0.1 | 11008 | FROZEN V1 | Implemented at both M1 ends | Display only
Advanced Visualisation | CoordinatorCD | ABSVisualisationPlantCD | VIZ_FILLER_A_STATUS | Integer | Display latest Filler A status | 127.0.0.1 | 11008 | FROZEN V1 | Implemented at both M1 ends | Display only
Advanced Visualisation | CoordinatorCD | ABSVisualisationPlantCD | VIZ_FILLER_B_STATUS | Integer | Display latest Filler B status | 127.0.0.1 | 11008 | FROZEN V1 | Implemented at both M1 ends | Display only
Advanced Visualisation | CoordinatorCD | ABSVisualisationPlantCD | VIZ_LID_STATUS | Integer | Display latest Lid status | 127.0.0.1 | 11008 | FROZEN V1 | Implemented at both M1 ends | Display only
Advanced Visualisation | CoordinatorCD | ABSVisualisationPlantCD | VIZ_CAPPER_STATUS | Integer | Display latest Capper status | 127.0.0.1 | 11008 | FROZEN V1 | Implemented at both M1 ends | Display only
Advanced Visualisation | CoordinatorCD | ABSVisualisationPlantCD | VIZ_UNLOADER_STATUS | Integer | Display latest Unloader status | 127.0.0.1 | 11008 | FROZEN V1 | Implemented at both M1 ends | Display only
Advanced Visualisation | CoordinatorCD | ABSVisualisationPlantCD | VIZ_REQUIRED_BOTTLES | Integer | Display current product-batch target | 127.0.0.1 | 11008 | FROZEN V1 | Implemented at both M1 ends | Display only
Advanced Visualisation | CoordinatorCD | ABSVisualisationPlantCD | VIZ_COMPLETED_BOTTLES | Integer | Display collected-bottle progress | 127.0.0.1 | 11008 | FROZEN V1 | Implemented at both M1 ends | Display only
M3 FT — M1 safety | FaultSupervisorCD | CoordinatorCD | FT_FAULT_ALERT | String | Record validated event; alert alone does not stop or resume production | 127.0.0.1 | 11001 | FROZEN V2.1 | M1 declaration/state/XML implemented; peer absent | No actuator control
M3 FT — M1 safety | FaultSupervisorCD | CoordinatorCD | FT_SAFE_STOP_REQUEST | String | Enter M1 coordination HOLD; request alone does not prove safe stop | 127.0.0.1 | 11001 | FROZEN V2.1 | M1 declaration/state/XML implemented; physical safe-stop confirmation missing | No premature ACK
M3 FT — M1 safety | FaultSupervisorCD | CoordinatorCD | FT_RECOVERY_READY | String | Record verified ready evidence; never auto-resume | 127.0.0.1 | 11001 | FROZEN V2.1 | M1 declaration/state/XML implemented; peer absent | HOLD retained
M3 FT — M1 safety | FaultSupervisorCD | CoordinatorCD | FT_RECOVERY_FAILED | String | Record/escalate failure and retain M1 HOLD | 127.0.0.1 | 11001 | FROZEN V2.1 | M1 declaration/state/XML implemented; peer absent | HOLD retained
M3 FT — M1 safety | CoordinatorCD | FaultSupervisorCD | FT_SAFE_STOP_ACK | String | Matching ACK only after independent physical safe-stop evidence | 127.0.0.1 | 13003 | FROZEN V2.1 | Declared/mapped; intentionally not emitted because safe-stop evidence boundary is missing | M1 only
M3 FT — M1 safety | CoordinatorCD | FaultSupervisorCD | FT_RESUME_DECISION | String | M1-only final RESUME or HOLD with event/reason | 127.0.0.1 | 13003 | FROZEN V2.1 | Declared/mapped; not emitted because exact M1 payload field order is undefined | M1 only
GP hand-off P1 | ConveyorControllerCD | RotaryTablePlantCD | LOAD_BOTTLE | String (bottleId) | Emit once after P1 stable and ID committed | 127.0.0.1 | 12003 | FROZEN V2.1 | M2 conceptual interface defined; M2/M3 SystemJ implementation pending | Bottle correlated
GP hand-off P2 | M4 Filler | RotaryTablePlantCD | MARK_FILLED | String (bottleId) | Emit once after required fill and sensor confirmation | 127.0.0.1 | 12003 | FROZEN V2.1 | Implemented at M4 sender and M3 RotaryTablePlantCD receiver; bottle-correlated completion only after both liquids are verified. | Bottle correlated
GP hand-off P3 | M3 Rotary | M3 Lid | BOTTLE_AT_LID_POSITION | String (bottleId) | Start Lid only for current filled P3 bottle |  | M3 internal | FROZEN V2.1 | Implemented within M3. | Bottle correlated
GP hand-off P3 | M3 Lid | M3 Rotary | LID_CYCLE_DONE | String (bottleId) | Completion after placement sensor confirmation |  | M3 internal | FROZEN V2.1 | Implemented within M3. | Bottle correlated
GP hand-off P4 | M4 Capper | RotaryTablePlantCD | MARK_CAPPED | String (bottleId) | Emit once after cap tightening and sensor confirmation | 127.0.0.1 | 12003 | FROZEN V2.1 | Implemented at M4 sender and M3 RotaryTablePlantCD receiver; bottle-correlated completion only after sensor-confirmed capping. | Bottle correlated
GP hand-off P6 | M3 Rotary | LabellerControllerCD | BOTTLE_AT_LABEL | String (bottleId) | Offer current P6 bottle for mandatory labelling | 127.0.0.1 | 11013 | FROZEN V2.1; M2 PORT ASSIGNED | M2 Labeller receiver moved to 11013 after M4 11011/11012 conflict check; implementation pending | No bypass
GP hand-off P6 | LabellerControllerCD | RotaryTablePlantCD | MARK_LABELLED | String (bottleId) | Accept only verified matching P6 label completion | 127.0.0.1 | 12003 | FROZEN V2.1 | M2 conceptual sender defined; M2/M3 SystemJ implementation pending | Reject stale/duplicate/wrong ID
GP hand-off P6 | BottleUnloaderControllerCD | RotaryTablePlantCD | P6_CLEAR | String (bottleId) | Emit only after removal and empty-sensor confirmation | 127.0.0.1 | 12003 | FROZEN V2.1 | M2 conceptual sender defined; M2/M3 SystemJ implementation pending | Both label + clear required
M3 FT — Transfer | M2TransferFaultAdapterCD | FaultSupervisorCD | TRANSFER_FAULT_EVENT | String | Versioned transfer fault event | 127.0.0.1 | 13003 | FROZEN V2.1 | M2 conceptual adapter interface defined; SystemJ/XML implementation pending
M3 FT — Transfer | FaultSupervisorCD | M2TransferFaultAdapterCD | TRANSFER_RECOVERY_REQUEST | String | One abstract policy-approved recovery action | 127.0.0.1 | 13002 | FROZEN V2.1; M2 PORT ASSIGNED | M2 assigns 13002; adapter implementation and end-to-end verification pending | Attempt 1 maximum
M3 FT — Transfer | M2TransferFaultAdapterCD | FaultSupervisorCD | TRANSFER_RECOVERY_ACK | String | ACCEPTED/REJECTED before any physical action | 127.0.0.1 | 13003 | FROZEN V2.1 | M2 conceptual adapter interface defined; SystemJ/XML implementation pending | Idempotent
M3 FT — Transfer | M2TransferFaultAdapterCD | FaultSupervisorCD | TRANSFER_RECOVERY_RESULT | String | SUCCESS/FAILED plus independent evidence | 127.0.0.1 | 13003 | FROZEN V2.1 | M2 conceptual adapter interface defined; SystemJ/XML implementation pending | Idempotent
Legacy FT GUI | FaultSupervisorCD | FaultManagementGUI | FT_GUI_STATUS | TBA | Proposal-only GUI status; not frozen by V2.1 |  | TBA | PROPOSED ONLY | No implementation in repository | Display only
Legacy FT GUI | FaultSupervisorCD | FaultManagementGUI | FT_EVENT_LOG | TBA | Proposal-only event log; not frozen by V2.1 |  | TBA | PROPOSED ONLY | No implementation in repository | Display only
Legacy FT GUI | FaultSupervisorCD | FaultManagementGUI | FT_RECOVERY_PROGRESS | TBA | Proposal-only progress; not frozen by V2.1 |  | TBA | PROPOSED ONLY | No implementation in repository | Display only
Legacy FT GUI | FaultManagementGUI | FaultSimulationPlantCD | GUI_FAULT_INJECTION | TBA | Proposal-only deterministic injection |  | TBA | PROPOSED ONLY | No implementation in repository | Test mode only
Machine Controller | CoordinatorCD | LabellerControllerCD | LABELLER_STATUS_REQUEST | pure signal | Read-only request for current Labeller status; never starts or advances labelling | 127.0.0.1 | 11013 | PROPOSED / TEAM ACCEPTANCE REQUIRED | Not implemented in M1: M2 production SystemJ/XML and a frozen Coordinator-facing Labeller monitoring contract are unavailable. | Polling only
Machine Controller | LabellerControllerCD | CoordinatorCD | LABELLER_STATUS | Integer | Latest Labeller status using shared 0..4 convention | 127.0.0.1 | 11001 | PROPOSED / TEAM ACCEPTANCE REQUIRED | Not implemented in M1: proposed conceptual sender only; peer source/XML and team acceptance are required. | Monitoring only
Advanced Visualisation | CoordinatorCD | ABSVisualisationPlantCD | VIZ_LABELLER_STATUS | Integer | Display latest Labeller Controller status only; no label-content telemetry | 127.0.0.1 | 11008 | PROPOSED / TEAM ACCEPTANCE REQUIRED | Not implemented: no approved Coordinator Labeller status source exists; current Advanced Visualisation remains on ten VIZ_* inputs. | Display only
M2 internal P6 | LabellerControllerCD | BottleUnloaderControllerCD | UNLOAD_READY | String (bottleId) | Permission to unload only after matching label verification; does not clear P6 or authorise rotation | 127.0.0.1 | 11010 | M2 MILESTONE 1 CONCEPTUAL | Defined in post-interview M2 design; implementation pending | Bottle correlated
M2 to M4 hand-off | BottleUnloaderControllerCD | SortPackControllerCD | BOTTLE_READY_FOR_SORT | String (full BottleContext) | Transfer the unchanged full BottleContext after verified labelled-bottle removal to M4 size-aware sorting and carton packing | 127.0.0.1 | 11012 | M4 V1.2 RECEIVER IMPLEMENTED; M2 PEER PENDING | M4 SortPack receiver/Plant path is implemented and tested; M2 Unloader sender and merged peer test remain pending. | Does not replace BOTTLE_DONE
M2 Controller/Plant | BottleLoaderControllerCD | BottleLoaderPlantCD | LOAD_CMD | String (bottleId) | Command one admission-controlled pick/place cycle for the assigned bottle | 127.0.0.1 | 12002 | M2 MILESTONE 1 CONCEPTUAL | Plant receiver port assigned by M2; implementation pending | Local actuation only
M2 Controller/Plant | BottleLoaderPlantCD | BottleLoaderControllerCD | LOAD_CONFIRMED | String (bottleId) | Sensor-confirmed bottle placement at the load point | 127.0.0.1 | 11002 | M2 MILESTONE 1 CONCEPTUAL | Controller receiver exists; implementation pending | Evidence required
M2 Controller/Plant | ConveyorControllerCD | ConveyorPlantCD | MOTOR_CMD | Boolean / pure pair | Enable or disable the entry conveyor motor under local interlocks | 127.0.0.1 | 12009 | M2 MILESTONE 1 CONCEPTUAL | Plant receiver port assigned by M2; implementation pending | Motor off on fault
M2 Controller/Plant | ConveyorPlantCD | ConveyorControllerCD | P1_FEEDBACK | String / sensor snapshot | P1 photo-eye, entry-clear and motor-stopped evidence used before LOAD_BOTTLE | 127.0.0.1 | 11009 | M2 MILESTONE 1 CONCEPTUAL | Controller receiver port assigned by M2; implementation pending | No inferred identity
M2 Controller/Plant | LabellerControllerCD | LabellerPlantCD | LABEL_CMD | String (bottleId¦labelData) | Generate and apply the label for the matching P6 bottle | 127.0.0.1 | 12013 | M2 MILESTONE 1 CONCEPTUAL | LabellerPlantCD moved to 12013 after M4 RecognitionPlantCD:12011 conflict check | Local actuation only
M2 Controller/Plant | LabellerPlantCD | LabellerControllerCD | LABEL_VERIFIED | String (bottleId¦result) | Independent result of label presence/content verification | 127.0.0.1 | 11013 | M2 MILESTONE 1 CONCEPTUAL | LabellerControllerCD moved to 11013 after M4 Registry/SortPack conflict check | Required before MARK_LABELLED
M2 Controller/Plant | BottleUnloaderControllerCD | BottleUnloaderPlantCD | UNLOAD_CMD | String (bottleId) | Remove the matching labelled bottle from P6 | 127.0.0.1 | 12010 | M2 MILESTONE 1 CONCEPTUAL | Plant receiver port assigned by M2; implementation pending | Local actuation only
M2 Controller/Plant | BottleUnloaderPlantCD | BottleUnloaderControllerCD | REMOVAL_CONFIRMED | String (bottleId¦p6Empty) | Physical-removal and empty-P6 sensor evidence | 127.0.0.1 | 11010 | M2 MILESTONE 1 CONCEPTUAL | Controller receiver exists; implementation pending | Required before P6_CLEAR/BOTTLE_DONE
M2 IP — Digital Twin | CoordinatorCD | DigitalTwinCD | TWIN_BATCH_CONTEXT | BatchContext object / String adapter | Initial order, product, recipe, quantity and profile context for product-instance twins | 127.0.0.1 | 14002 | M2 IP CONCEPTUAL / M1 NO IMPLEMENTATION | No frozen payload/transport or M2 implementation is available; do not add this IP-only output to M1 yet. | Informational only
M2 IP — Digital Twin | M2/M3/M4 bottle-event owners | DigitalTwinCD | WORKPIECE_TWIN_UPDATE | WorkpieceTwinUpdate object / String adapter | Update the bottle/workpiece identity, P1..P6 position, lifecycle, label and completion history | 127.0.0.1 | 14002 | M2 MILESTONE 1 CONCEPTUAL | BottleTwin is a bottle-specific alias of WorkpieceTwin; implementation pending | Idempotent by workpieceId/event
M2 IP — Digital Twin | M2/M3/M4 Controllers/Plants | DigitalTwinCD | RESOURCE_TWIN_UPDATE | ResourceTwinUpdate object / String adapter | Update explicit Loader/Conveyor/Rotary/Filler/Lid/Capper/Labeller/Unloader/SortPack twin state | 127.0.0.1 | 14002 | M2 MILESTONE 1 CONCEPTUAL | Final publisher set and schema require team confirmation | No actuator authority
M2 IP — Digital Twin | Coordinator/Visualisation/Controllers | DigitalTwinCD | TWIN_CONTEXT_REQUEST | String (workpieceId/resourceId) | Read-only request for correlated product and resource context | 127.0.0.1 | 14002 | M2 MILESTONE 1 CONCEPTUAL | Query API/transport pending | Read only
M2 IP — Digital Twin | DigitalTwinCD | Requesting read-only client | TWIN_CONTEXT_SNAPSHOT | TwinContext snapshot | Return immutable workpiece and resource snapshots; never commands Plant state | Consumer-owned / TBA | Consumer-owned / TBA | M2 MILESTONE 1 CONCEPTUAL | Consumer mappings and transport pending | Read only
M2 IP — Digital Twin | DigitalTwinCD | ReadOnlyTwinViewer | ACTIVE_TWINS_SNAPSHOT | CombinedTwinSnapshot | Read-only list of active workpiece and resource twins for IP demonstration | 127.0.0.1 | TBA / M2 supplies at implementation | M2 MILESTONE 1 CONCEPTUAL | Viewer boundary is separate from frozen M1 visualisation; implementation pending | Display only
M2 transport safety | M2TransferFaultAdapterCD | M2 owning Controller | LOCAL_RECOVERY_INTENT | Internal typed event | Adapter passes an accepted abstract intent to the owning M2 Controller; Controller rechecks local safety | M2 internal | M2 internal | M2 MILESTONE 1 CONCEPTUAL | Internal adapter/Controller boundary to be implemented | No delegated actuator authority
M2 transport safety | M2 owning Controller | M2TransferFaultAdapterCD | LOCAL_RECOVERY_EVIDENCE | Internal typed result | Return sensor-confirmed safe/service evidence for ACK/result generation | M2 internal | 13002 / internal | M2 MILESTONE 1 CONCEPTUAL | Internal evidence boundary to be implemented | Failed sensor cannot verify itself
M4 V1.2 to M2 | BottleContextRegistryCD | BottleLoaderControllerCD | LOAD_PROFILE | String (full BottleContext) | Provide validated bottle identity, size, capacity, geometry and packaging profile before admission | 127.0.0.1 | 11002 | M4 V1.2 SENDER IMPLEMENTED; M2 PEER PENDING | M4 Registry sender validates and transmits the full context; M2 Loader receiver remains pending. | No competing registry
M4 V1.2 to M2 | BottleContextRegistryCD | BottleUnloaderControllerCD | UNLOAD_PROFILE | String (full BottleContext) | Provide the unchanged context for the matching bottle before downstream SortPack hand-off | 127.0.0.1 | 11010 | M4 V1.2 SENDER IMPLEMENTED; M2 PEER PENDING | M4 Registry sender validates and transmits the full context; M2 Unloader receiver remains pending. | Bottle correlated
M4 Recognition | RecognitionPlantCD | BottleContextRegistryCD | BOTTLE_RECOGNISED | String (bottleId¦sizeCode¦capacityMl) | Create one validated context for a new bottleId; reject unknown size or capacity mismatch | 127.0.0.1 | 11011 | M4 V1.2 IMPLEMENTED | RecognitionPlantCD and BottleContextRegistryCD endpoints are implemented; the real recognition algorithm remains out of scope. | No actuator action on invalid context
M4 Registry to M3 | BottleContextRegistryCD | RotaryTableControllerCD | ROTARY_BOTTLE_CONTEXT | String (full BottleContext) | Provide the single validated bottle context to M3 for P2/P4 correlation | 127.0.0.1 | 11003 | M4/M3 IMPLEMENTED | M4 Registry sender and M3 Rotary receiver use the unchanged full BottleContext. | Not an M1 Coordinator signal
M3 to M4 P2 start | M3 Rotary | FillerAControllerCD | BOTTLE_AT_FILL | String (full BottleContext) | Start filling only for the same bottleId physically confirmed at Position 2 | 127.0.0.1 | 11004 | M4/M3 IMPLEMENTED | M3 same-bottle P2 relay and M4 Filler A receiver are implemented. | Reject stale, duplicate, malformed or mismatched context
M4 internal A to B | FillerAControllerCD | FillerBControllerCD | FILL_A_DONE | String (full BottleContext¦measuredAMl) | Release Filler B only after all A outputs are safe and measured A is acceptable | 127.0.0.1 | 11005 | M4 INTERNAL IMPLEMENTED | Implemented idempotent full-context plus measuredAMl hand-off; Filler B remains closed on mismatch. | Filler B remains closed on mismatch
M4 to M3 P2 done | FillerBControllerCD | RotaryTablePlantCD | MARK_FILLED | String (bottleId) | Emit exactly once after both liquids are verified | 127.0.0.1 | 12003 | FROZEN M3 V2.1; M4/M3 IMPLEMENTED | M4 sender and M3 Plant receiver are implemented; duplicate transport copies do not repeat physical work. | Bottle correlated; never BOTTLE_DONE
M3 to M4 P4 start | M3 Rotary | CapperControllerCD | BOTTLE_AT_CAP | String (full BottleContext) | Start the geometry-aware cap sequence only for the matching bottle at Position 4 | 127.0.0.1 | 11007 | M4/M3 IMPLEMENTED | M3 same-bottle P4 relay and M4 Capper receiver are implemented. | Reject stale, duplicate, malformed or mismatched context
M4 to M3 P4 done | CapperControllerCD | RotaryTablePlantCD | MARK_CAPPED | String (bottleId) | Emit exactly once after cap tightening and sensor confirmation | 127.0.0.1 | 12003 | FROZEN M3 V2.1; M4/M3 IMPLEMENTED | M4 sender and M3 Plant receiver are implemented; completion follows the full safe Capper sequence. | Bottle correlated; never BOTTLE_DONE
M4 SortPack local | SortPackControllerCD | SortPackPlantCD | SET_SORT_LANE / PLACE_BOTTLE | M4-local commands | Select the S/L route and place the bottle; count only after expected-lane and placement feedback | 127.0.0.1 | 12012 | M4 V1.2 IMPLEMENTED | M4 Controller/Plant lane selection, placement confirmation and package counting are implemented and tested. | No count on wrong lane or missing package

## Ports
Current Master Receiver Ports and V2.1 Transition
Component / Boundary | Clock Domain | Receiver Port | IP | Contract Status | Implementation / Constraint
POS | POSCD | 11000 | 127.0.0.1 | FROZEN V1 | Implemented
ABS Coordinator | CoordinatorCD | 11001 | 127.0.0.1 | FROZEN V1 + V2.1 FT inputs | Implemented; one shared SimpleServer
Bottle Loader Controller | BottleLoaderControllerCD | 11002 | 127.0.0.1 | FROZEN V1 | M1 mapping implemented; peer absent
M2 Conveyor status receiver | ConveyorControllerCD | 11009 | 127.0.0.1 | FROZEN V2.1; M2 PORT ASSIGNED | M1 production XML now targets ConveyorControllerCD:11009; peer implementation pending/unavailable.
M3 Rotary Table Controller | RotaryTableControllerCD | 11003 | 127.0.0.1 | FROZEN V2.1; M1 MAPPING ALIGNED | Implemented; M1 production XML and M3 receiver are aligned.
Filler A Controller | FillerAControllerCD | 11004 | 127.0.0.1 | FROZEN V1 | Implemented M4 Controller receiver; M1 mapping aligned.
Filler B Controller | FillerBControllerCD | 11005 | 127.0.0.1 | FROZEN V1 | Implemented M4 Controller receiver; M1 mapping aligned.
Lid Loader Controller | LidLoaderControllerCD | 11006 | 127.0.0.1 | FROZEN V2.1 | Implemented M3 Controller receiver; M1 mapping aligned.
Capper Controller | CapperControllerCD | 11007 | 127.0.0.1 | FROZEN V1 | Implemented M4 Controller receiver; M1 mapping aligned.
Advanced ABS Visualisation | ABSVisualisationPlantCD | 11008 | 127.0.0.1 | FROZEN V1 | Implemented; display-only
Bottle Unloader Controller | BottleUnloaderControllerCD | 11010 | 127.0.0.1 | FROZEN V1 | M1 mapping implemented; peer absent
M3 Rotary Table Plant | RotaryTablePlantCD | 12003 | 127.0.0.1 | FROZEN V2.1 | Implemented M3 Plant receiver; M4 MARK_FILLED/MARK_CAPPED mappings aligned.
M3 Lid Loader Plant | LidLoaderPlantCD | 12006 | 127.0.0.1 | FROZEN V2.1 | Implemented M3 Plant receiver.
M3 Fault Supervisor | FaultSupervisorCD | 13003 | 127.0.0.1 | FROZEN V2.1 | Implemented M3 Fault Supervisor; M2 Transfer Adapter peer remains pending.
M2 Transfer Fault Adapter | M2TransferFaultAdapterCD | 13002 | 127.0.0.1 | FROZEN V2.1; M2 PORT ASSIGNED | Receives TRANSFER_RECOVERY_REQUEST; implementation pending
M2 Labeller P6 receiver | LabellerControllerCD | 11013 | 127.0.0.1 | FROZEN V2.1; M2 PORT ASSIGNED | M2 Labeller moved from 11011 to avoid M4 Registry 11011 / SortPack 11012; implementation pending
FaultSimulationPlantCD | FaultSimulationPlantCD | TBA |  | PROPOSED ONLY | Not frozen by M3-facing V2.1; test mode only
FaultManagementGUI boundary | TBA | TBA |  | PROPOSED ONLY | Transport/port not frozen by M3-facing V2.1
M2 Bottle Loader Plant | BottleLoaderPlantCD | 12002 | 127.0.0.1 | M2 MILESTONE 1 CONCEPTUAL | Receives LOAD_CMD; M2 implementation pending
M2 Conveyor Plant | ConveyorPlantCD | 12009 | 127.0.0.1 | M2 MILESTONE 1 CONCEPTUAL | Receives MOTOR_CMD; M2 implementation pending
M2 Labeller Plant | LabellerPlantCD | 12013 | 127.0.0.1 | M2 MILESTONE 1 CONCEPTUAL | M2 Labeller Plant moved from 12011 to avoid M4 RecognitionPlant 12011 / SortPackPlant 12012
M2 Bottle Unloader Plant | BottleUnloaderPlantCD | 12010 | 127.0.0.1 | M2 MILESTONE 1 CONCEPTUAL | Receives UNLOAD_CMD; M2 implementation pending
M2 Digital Twin IP | DigitalTwinCD | 14002 | 127.0.0.1 | M2 MILESTONE 1 CONCEPTUAL | Receives batch, workpiece and resource-twin updates/queries; final transport schema pending
M4 Sort/Pack dependency | SortPackControllerCD | 11012 | 127.0.0.1 | M4 V1.2 IMPLEMENTED; M2 PEER PENDING | M4 receiver and local SortPack path implemented; M2 BOTTLE_READY_FOR_SORT sender pending.
M4 BottleContext Registry | BottleContextRegistryCD | 11011 | 127.0.0.1 | M4 V1.2 IMPLEMENTED | Implemented receiver for validated BOTTLE_RECOGNISED and full-context distribution.
M4 Recognition Plant | RecognitionPlantCD | 12011 | 127.0.0.1 | M4 V1.2 IMPLEMENTED | Implemented M4 recognition source Plant; recognition algorithm remains conceptual/out of scope.
M4 SortPack Plant | SortPackPlantCD | 12012 | 127.0.0.1 | M4 V1.2 IMPLEMENTED | Implemented M4 SortPack Plant receiver.
M4 Filler Plants | FillerAPlantCD / FillerBPlantCD | 12004 / 12005 | 127.0.0.1 | M4 V1.2 IMPLEMENTED | Implemented M4 Filler A/B Plant receivers.
M4 Capper Plant | CapperPlantCD | 12007 | 127.0.0.1 | M4 V1.2 IMPLEMENTED | Implemented M4 Capper Plant receiver.

## Payloads
Interface Payload Formats
Family | Payload / Signal | Canonical Format | Example / Rule | Status
POS V1 | ORDER | orderId¦productCount¦product1;product2;product3;product4 | PO001¦2¦P1,60,40,5;P2,30,70,3 | FROZEN V1
POS V1 | Product | productId,liquidARatio,liquidBRatio,quantity | P1,60,40,5 | FROZEN V1
POS V1 | ORDER_COMPLETE | orderId¦COMPLETED¦completionTime | PO001¦COMPLETED¦4 | FROZEN V1
GP V2.1 | P1/P2/P3/P4/P6 bottle hand-offs | String value = bottleId | B104; stale/duplicate/wrong-bottle events rejected | FROZEN V2.1
M3 FT V2.1 | TRANSFER_FAULT_EVENT | V2¦eventId¦sourceEpoch¦subsystem¦faultCode¦severity¦bottleId¦stateVersion | V2¦F021¦E07¦TRANSFER¦ARRIVAL_TIMEOUT¦WARNING¦B104¦18 | FROZEN V2.1
M3 FT V2.1 | TRANSFER_RECOVERY_REQUEST | V2¦eventId¦sourceEpoch¦action¦attempt¦expectedStateVersion | V2¦F021¦E07¦RETRY_TRANSFER¦1¦18 | FROZEN V2.1; M2 receiver 13002 assigned
M3 FT V2.1 | TRANSFER_RECOVERY_ACK | V2¦eventId¦sourceEpoch¦attempt¦ack¦reason¦acceptedStateVersion | V2¦F021¦E07¦1¦ACCEPTED¦route_clear¦18 | FROZEN V2.1
M3 FT V2.1 | TRANSFER_RECOVERY_RESULT | V2¦eventId¦sourceEpoch¦attempt¦outcome¦safeEvidence¦serviceEvidence¦resultingStateVersion | V2¦F021¦E07¦1¦SUCCESS¦motor_off+occupancy_consistent¦arrival_confirmed¦19 | FROZEN V2.1
M3 FT V2.1 | M1 safety messages | Exact String field order is NOT DEFINED by supplied V2.1 | Signals/semantics are frozen; do not invent an incompatible parser | SCHEMA GAP
V2.1 Field and Identity Rules
Field | Rule
eventId | Unique and stable for the event/recovery lifecycle
sourceEpoch | Publisher boot/session ID; new registered epoch invalidates older in-flight events
stateVersion | Monotonic Controller-owned recovery-state version within one sourceEpoch
attempt | Supervisor-owned physical attempt number; attempt 1 is the maximum
bottleId | Required when known; use '-' when unavailable; never infer an identity
evidence | Independent safe/service observation; failed sensor cannot verify itself
V2.1 Parsing / Idempotency
Condition | Receiver behaviour
Duplicate eventId + attempt | Return previous ACK/result; never repeat physical work
Inactive sourceEpoch | Reject STALE_EPOCH; no action
Lower stateVersion | Reject STALE_STATE
Unexpected higher stateVersion | Do not execute; request fresh state snapshot
ACK timeout | Fail request; do not silently resend physical attempt
Result timeout / invalid evidence | Report FT_RECOVERY_FAILED
Legacy proposal payloads
SUPERSEDED | FaultEventV1 / RecoveryRequestV1 / RecoveryResultV1 / CoordinatorDecisionV1 | Retained only in Markdown migration history | Not current for explicitly superseded M3-facing V2.1 boundaries | SUPERSEDED
M2 GP | UNLOAD_READY | String value = bottleId | B104; internal permission only after label verification; does not clear P6 | M2 MILESTONE 1 CONCEPTUAL
M2 → M4 | BOTTLE_READY_FOR_SORT | bottleId¦sizeCode¦capacityMl¦geometryProfileId¦packagingProfileId | B105¦L¦500¦GEOM_L¦PACK_L; M2 preserves unchanged; SortPack receiver 11012 | M4 V1.2 PROPOSED; M2 APPROVES
M2 Controller/Plant | Plant commands | LOAD_CMD / MOTOR_CMD / LABEL_CMD / UNLOAD_CMD | Typed local commands; only owning Controller issues actuation | M2 MILESTONE 1 CONCEPTUAL
M2 Controller/Plant | Plant evidence | LOAD_CONFIRMED / P1_FEEDBACK / LABEL_VERIFIED / REMOVAL_CONFIRMED | Bottle-correlated physical/sensor evidence; no completion inferred from status polling | M2 MILESTONE 1 CONCEPTUAL
M2 IP — Digital Twin | TWIN_BATCH_CONTEXT | BatchContext{orderId,productId,ratios,quantity,profileRef} | Initial metadata; exact serialisation/typed-channel choice pending | M2 MILESTONE 1 CONCEPTUAL
M2 IP — Digital Twin | WORKPIECE_TWIN_UPDATE | WorkpieceTwinUpdate{workpieceId,eventType,data,time} | BottleTwin is an alias for the bottle/product-instance WorkpieceTwin | M2 MILESTONE 1 CONCEPTUAL
M2 IP — Digital Twin | RESOURCE_TWIN_UPDATE | ResourceTwinUpdate{resourceId,resourceType,linkedWorkpieceId,status,context,time} | One explicit twin per production resource; no direct actuation | M2 MILESTONE 1 CONCEPTUAL
M2 IP — Digital Twin | TWIN_CONTEXT_REQUEST / SNAPSHOT | request(workpieceId/resourceId) → immutable TwinContext | Read/query only; consumer mapping and final transport pending | M2 MILESTONE 1 CONCEPTUAL
Cross-team approval summary — M4/M2 | Full BottleContext | bottleId¦sizeCode¦capacityMl¦geometryProfileId¦packagingProfileId | Only S¦200¦GEOM_S¦PACK_S or L¦500¦GEOM_L¦PACK_L | M4 IMPLEMENTED; M2 PEER APPROVED/PENDING
Cross-team approval summary — M4 -> M2 | LOAD_PROFILE / UNLOAD_PROFILE | Full BottleContext | Registry sends unchanged context to M2 Loader:11002 / Unloader:11010 | M4 SENDER IMPLEMENTED; M2 RECEIVERS PENDING
Cross-team approval summary — M2 -> M4 | BOTTLE_READY_FOR_SORT | Full BottleContext | M2 Unloader sends unchanged context to SortPackControllerCD:11012 after verified removal | M4 RECEIVER IMPLEMENTED; M2 SENDER PENDING
Note | Rows 42–44 summarize receiver-owner approvals; canonical M4 payload definitions follow below.
M4 V1.2 Canonical Payloads
Family | Payload / Signal | Canonical Format | Example / Rule | Status
M4 Recognition | BOTTLE_RECOGNISED | bottleId¦sizeCode¦capacityMl | B104¦S¦200 | M4 V1.2 IMPLEMENTED
M4 Registry to M2 | LOAD_PROFILE / UNLOAD_PROFILE | bottleId¦sizeCode¦capacityMl¦geometryProfileId¦packagingProfileId | B104¦S¦200¦GEOM_S¦PACK_S | M4 IMPLEMENTED; M2 PEER PENDING
M4 Registry to M3 | ROTARY_BOTTLE_CONTEXT | bottleId¦sizeCode¦capacityMl¦geometryProfileId¦packagingProfileId | M4 Registry sender and M3 RotaryTableControllerCD:11003 receiver implemented. | M4/M3 IMPLEMENTED
M3 to M4 | BOTTLE_AT_FILL / BOTTLE_AT_CAP | bottleId¦sizeCode¦capacityMl¦geometryProfileId¦packagingProfileId | B105¦L¦500¦GEOM_L¦PACK_L | M4/M3 IMPLEMENTED
M4 internal | FILL_A_DONE | bottleId¦sizeCode¦capacityMl¦geometryProfileId¦packagingProfileId¦measuredAMl | B104¦S¦200¦GEOM_S¦PACK_S¦120 | M4 INTERNAL IMPLEMENTED
M4 to M3 | MARK_FILLED / MARK_CAPPED | bottleId | B104; receiver RotaryTablePlantCD:12003 | FROZEN M3 V2.1; M4/M3 IMPLEMENTED
M2 to M4 | BOTTLE_READY_FOR_SORT | bottleId¦sizeCode¦capacityMl¦geometryProfileId¦packagingProfileId | B105¦L¦500¦GEOM_L¦PACK_L; preserve unchanged | M4 RECEIVER IMPLEMENTED; M2 SENDER PENDING
M4 encoding | Numeric fields | 0 or [1-9][0-9]* | ASCII pipe-delimited; no sign, decimal point or leading zero | M4 V1.2 IMPLEMENTED
M4 profiles | Allowed mappings | S¦200¦GEOM_S¦PACK_S or L¦500¦GEOM_L¦PACK_L | No other size/capacity/profile combination is valid | M4 V1.2 IMPLEMENTED
M4 filling | measuredAMl | Unsigned integer mL in 0..capacityMl | Must satisfy target/tolerance and measuredAMl + targetB = capacityMl within tolerance | M4 V1.2 IMPLEMENTED
M1 to M4 | FILL_A_RATIO / FILL_B_RATIO | Separate Integer signals, each 0..100 | CONFIRMED in current M1 OrderV1 validation before Coordinator dispatch; M4 does not claim pre-dose visibility of both values | CONFIRMED M1/M4 IMPLEMENTATION
M4 filling | targetAMl / targetBMl | targetAMl = capacityMl × ratioA / 100; targetBMl = capacityMl × ratioB / 100 | For S=200 and L=500 with Integer ratios, results are integral mL; no rounding is permitted | M4 V1.2 IMPLEMENTED
M4 identity | bottleId | Non-empty, case-sensitive ASCII token; no '¦', CR, LF or leading/trailing whitespace | Preserve byte-for-byte through Recognition, Registry, M2, M3 and M4; reject malformed identity before physical action | M4 V1.2 IMPLEMENTED

## FT Details
M3-facing Fault-Tolerance V2.1 — Frozen Contract and M1 Implementation
STATUS: FROZEN (effective 28 August 2026); implementation tracked separately
Item | Contract Status | Implementation Status | Owner / Blocker
M1 four FT inputs | FROZEN V2.1 | IMPLEMENTED — declarations, state recording, XML mapping to 11001 | M1
M1 FT_SAFE_STOP_ACK | FROZEN V2.1 | DECLARED/MAPPED via OptionalSimpleClient; NOT EMITTED | Independent physical safe-stop evidence boundary missing
M1 FT_RESUME_DECISION | FROZEN V2.1 | DECLARED/MAPPED via OptionalSimpleClient; NOT EMITTED | Exact M1 String payload field order missing
FaultSupervisorCD:13003 | FROZEN V2.1 | IMPLEMENTED in M3 source/XML; M1 mappings aligned | M3
M2 Transfer Fault Adapter | Signal/payload FROZEN | Conceptual M2 adapter boundary defined; receiver 13002 assigned; implementation pending | M2
Current M1 safe-stop capability | ACK requires genuine safe stop | Coordination HOLD only; no actuator or physical-stop confirmation | Do not fake ACK
M1 Safety Behaviour
Input / event | Required behaviour | Current M1 result | Safety note
FT_FAULT_ALERT | Record validated event only | Recorded; no HOLD change | Does not cancel order or drive actuator
FT_SAFE_STOP_REQUEST | Coordinate safe stop and ACK only when proven | Records request; holds new order/next batch; no ACK | Current order may still be physically active
FT_RECOVERY_READY | Record verified evidence; no auto-resume | Recorded; HOLD retained | M1 alone decides RESUME/HOLD
FT_RECOVERY_FAILED | Record/escalate and hold | Recorded; HOLD retained | No automatic retry/resume
Recovery Policy V2.1
Subsystem / fault | Automatic action | Evidence / terminal behaviour | Status
Rotary ALIGNMENT_TIMEOUT | No automatic REHOME | Motor off; M1-held safe stop + manual position/bottle reconciliation without absolute evidence | FROZEN
Rotary MOTOR_STALL / POSITION_SENSOR_FAILURE | No automatic motion | Safe stop/isolate; failed sensor cannot prove recovery | FROZEN
Lid MAGAZINE_EMPTY | WAIT_RESOURCE; no attempt consumed | Independent magazine-available confirmation | FROZEN
Lid PICK_TIMEOUT | At most one RETRY_PICK | Actuator-home + no-lid-held + lid-available before ACCEPTED | FROZEN
Lid PLACEMENT_TIMEOUT / LID_SENSOR_FAULT | No blind retry | Isolate/reconcile with independent placement evidence | FROZEN
Transfer ARRIVAL_TIMEOUT | At most one RETRY_TRANSFER | Route-clear + occupancy before ACK; arrival evidence for result | FROZEN
Transfer DEPARTURE_TIMEOUT / PHOTO_EYE_FAILURE / POSITION_CONFLICT | No blind restart | Reconcile bottle identity/location before later operation | FROZEN
Correlation and Idempotency
Condition | Receiver action | Physical-work rule | Status
Duplicate eventId + attempt | Return prior ACK/result | Never repeat physical work | FROZEN
Inactive sourceEpoch | STALE_EPOCH | No action | FROZEN
Lower stateVersion | STALE_STATE | No action | FROZEN
Unexpected higher stateVersion | Request fresh snapshot | Do not execute | FROZEN
ACK timeout | Fail request | No silent resend | FROZEN
Invalid result/evidence | FT_RECOVERY_FAILED | No resume | FROZEN
Concurrent faults | One active recovery/subsystem; critical pre-empts warnings | Deterministic | FROZEN
Reference Sequence
1 | Controller/Adapter publishes correlated event | eventId + sourceEpoch + stateVersion
2 | FaultSupervisor validates schema, identity, epoch/version and eligibility | No actuator action
3 | Supervisor sends FT_FAULT_ALERT and, when needed, FT_SAFE_STOP_REQUEST | Alert alone is observational
4 | M1 sends matching FT_SAFE_STOP_ACK only after genuine safe stop | Current M1 cannot yet satisfy this
5 | Supervisor sends one eligible request with attempt=1 | Maximum physical attempt
6 | Owning adapter ACKs ACCEPTED/REJECTED before physical action | Duplicate returns prior response
7 | Owning adapter executes once and returns independent evidence | Failed sensor cannot self-verify
8 | Supervisor sends FT_RECOVERY_READY or FT_RECOVERY_FAILED | Never resumes global production
9 | M1 alone sends final RESUME or HOLD | Exact M1 payload field order still required
Open Integration Blockers
RESOLVED AT M1 — CONVEYOR/ROTARY STATUS MAPPING ALIGNED | Use ConveyorControllerCD:11009 and RotaryTableControllerCD:11003 as the separate status receivers. | M1 and M3 production XML is aligned; M2 Conveyor peer remains unavailable. | M1 + M2 + M3 integration
RESOLVED — M2 Transfer Fault Adapter receiver assigned | 13002 | TRANSFER_RECOVERY_REQUEST can now be mapped; implementation/test remains | M2 + M3 integration
Rotary Clock Domain mapping | V2.1 receiver is RotaryTableControllerCD:11003 | Current M1 production XML and M3 RotaryTableControllerCD:11003 implementation match. | M3 implemented; merged M2 pipeline still pending
Exact M1 FT payload field order | Not defined by supplied V2.1 | ACK/decision emission withheld; no parser invented | M1 + M3 agreement

## Status Codes
System Status Codes
Value | Meaning | Status
0 | IDLE | FROZEN V1
1 | READY | FROZEN V1
2 | BUSY | FROZEN V1
3 | DONE | FROZEN V1
4 | FAULT | FROZEN V1
Note | WAITING is only the initial GUI label before a status is received; it is not code 5.
Polling | Every *_STATUS_REQUEST is read-only and must not start, acknowledge, reset or advance a physical operation.

## Contract Check
Boundary / receiver | Owner | Final candidate port | Source contract | Check result | Required follow-up
ConveyorControllerCD | M2 | 11009 | M2 V1.0 + M3 V2.1 | PASS AT M1 — PRODUCTION MAPPING ALIGNED | Verify real M2 Conveyor source/XML and merged-runtime behaviour
M3 Rotary Controller receiver | M1 / M3 | 11003 | M1 V1 + M3 V2.1 + M4 V1.2 | PASS — M1/M3 FROZEN RECEIVER AND FULL-CONTEXT PATH IMPLEMENTED | Retain current XML and verify the final merged M2 pipeline
LabellerControllerCD | M2 | 11013 | M2 V1.0 | PASS — moved from conflict | M3 maps BOTTLE_AT_LABEL; Coordinator status polling remains proposed pending team acceptance
BottleContextRegistryCD | M4 | 11011 | M4 V1.2 | PASS — M4 IMPLEMENTED AT 11011 | M4 model/SystemJ tests pass; M2 profile peers remain pending
SortPackControllerCD | M4 | 11012 | M4 V1.2 | PASS — M4 IMPLEMENTED AT 11012 | M4 SortPack path passes; verify M2 Unloader sender when available
LabellerPlantCD | M2 | 12013 | M2 V1.0 | PASS — moved from M4 12011/12012 | M2 implement Plant XML
RecognitionPlantCD / SortPackPlantCD | M4 | 12011 / 12012 | M4 V1.2 | PASS — M4 PLANTS IMPLEMENTED AT 12011 / 12012 | Covered by M4 model and SystemJ demo
M2TransferFaultAdapterCD | M2 | 13002 | M2 V1.0 + M3 V2.1 | PASS — paired with M3 13003 | M2/M3 implement and test V2 parser/evidence
FaultSupervisorCD | M3 | 13003 | M3 V2.1 | PASS — frozen receiver | M3 implementation present; full M2/M3 fault test remains pending
DigitalTwinCD | M2 IP | 14002 | M2 V1.0 | PASS — separate IP range | Freeze exact update/query transport before implementation
LOAD_PROFILE / UNLOAD_PROFILE | M4 -> M2 | 11002 / 11010 | M4 V1.2 + M2 V1.0 | M4 SENDER IMPLEMENTED; M2 RECEIVERS PENDING | Verify M2 validation and unchanged forwarding when its implementation arrives
BOTTLE_READY_FOR_SORT | M2 -> M4 | 11012 | M4 V1.2 + M2 V1.0 | M4 RECEIVER IMPLEMENTED; M2 SENDER PENDING | Verify merged M2 Unloader-to-M4 SortPack hand-off
LABELLER_STATUS_REQUEST / STATUS | M1 <-> M2 | 11013 / 11001 | M2 V1.0 | PROPOSED — NOT IMPLEMENTED IN M1 | Team/M2 must freeze the Coordinator-facing monitoring boundary and provide peer source/XML before M1/VIZ changes
FILL_A_RATIO / FILL_B_RATIO pair invariant | M1 -> M4 | 11004 / 11005 | M1 V1 + M4 V1.2 | PASS — M1 VALIDATION AND M4 CONTROLLERS IMPLEMENTED | Covered by OrderV1 and Member4ModelSelfTest
ROTARY_BOTTLE_CONTEXT | M4 -> M3 | 11003 | M4 V1.2 | PASS — M4/M3 FULL-CONTEXT PATH IMPLEMENTED | No Coordinator declaration; retain exact payload and port
BOTTLE_AT_FILL / BOTTLE_AT_CAP | M3 -> M4 | 11004 / 11007 | M4 V1.2 | PASS — M3/M4 SAME-BOTTLE P2/P4 RELAYS IMPLEMENTED | Covered by Member3Member4IntegrationSelfTest and the M4 two-size SystemJ demo
MARK_FILLED / MARK_CAPPED | M4 -> M3 | 12003 | M3 V2.1 + M4 V1.2 | PASS — M4 SENDERS AND M3 PLANT RECEIVER IMPLEMENTED | Retain bottle correlation and idempotent bounded transport
BOTTLE_DONE ownership | M2 -> M1 | 11001 | M1 V1 + M4 V1.2 | PASS — M2 remains exclusive owner | M2 implements one bounded BOTTLE_DONE PRESENT window plus an ABSENT gap per bottle; verify edge-counting with the real Unloader.

## GP Hand-offs
GP Bottle-Correlated Hand-offs — M3 V2.1 + M4 V1.2
Machine/Plant and bottle-context hand-offs; none belongs in CoordinatorCD unless explicitly shown in the frozen M1 boundary.
Stage | Sender | Receiver | Signal | Type | Receiver Port | Acceptance Rule | Implementation / Owner
P1 | ConveyorControllerCD | RotaryTablePlantCD | LOAD_BOTTLE | String (bottleId) | 12003 | Once after P1 stable and ID committed | FROZEN; M2 conceptual sender defined — implementation pending
P2 | M4 Filler | RotaryTablePlantCD | MARK_FILLED | String (bottleId) | 12003 | Once after required fill and sensor confirmation | FROZEN; implemented at M4 sender and M3 receiver
P3 | M3 Rotary | M3 Lid | BOTTLE_AT_LID_POSITION | String (bottleId) | M3 internal | Current filled P3 bottle only | FROZEN; implemented within M3
P3 | M3 Lid | M3 Rotary | LID_CYCLE_DONE | String (bottleId) | M3 internal | After placement sensor confirmation | FROZEN; implemented within M3
P4 | M4 Capper | RotaryTablePlantCD | MARK_CAPPED | String (bottleId) | 12003 | Once after cap tightening and sensor confirmation | FROZEN; implemented at M4 sender and M3 receiver
P6 | M3 Rotary | LabellerControllerCD | BOTTLE_AT_LABEL | String (bottleId) | 11013 | Mandatory labelling; no bypass | FROZEN M3 signal; M2 port 11013 assigned after M4 conflict check
P6 | LabellerControllerCD | RotaryTablePlantCD | MARK_LABELLED | String (bottleId) | 12003 | Matching current P6 bottle; reject stale/duplicate/wrong ID | FROZEN; M2 conceptual sender defined — implementation pending
P6 | BottleUnloaderControllerCD | RotaryTablePlantCD | P6_CLEAR | String (bottleId) | 12003 | After physical removal + empty sensor; matching bottle ID | FROZEN; M2 conceptual sender defined — implementation pending
P6 internal M2 | LabellerControllerCD | BottleUnloaderControllerCD | UNLOAD_READY | String (bottleId) | 11010 | Only after matching label verification; does not clear P6 | M2 conceptual interface — implementation pending
P6 gate | Next rotation is blocked until both MARK_LABELLED(bottleId) and P6_CLEAR(bottleId) match the current P6 bottle.
Validation | Reject stale, duplicate or wrong-bottle events. Labelling is always enabled in the V2.1 baseline.
Post-P6 | BottleUnloaderControllerCD | SortPackControllerCD | BOTTLE_READY_FOR_SORT | String (full BottleContext) | 11012 | After verified labelled-bottle removal; preserve full context; does not replace BOTTLE_DONE | M4 receiver/Plant implemented; M2 Unloader sender pending
Recognise | RecognitionPlantCD | BottleContextRegistryCD | BOTTLE_RECOGNISED | String (bottleId¦sizeCode¦capacityMl) | 11011 | Create once for a new valid bottleId; reject unknown size/capacity mismatch | M4 V1.2 implemented
Track | BottleContextRegistryCD | RotaryTableControllerCD | ROTARY_BOTTLE_CONTEXT | String (full BottleContext) | 11003 | Forward the unchanged validated full context; not an M1 Coordinator signal | Implemented at M4 Registry sender and M3 Rotary receiver
P2 start | M3 Rotary | FillerAControllerCD | BOTTLE_AT_FILL | String (full BottleContext) | 11004 | Same bottleId physically confirmed at Position 2 | Implemented at M3 sender and M4 Filler A receiver
A -> B | FillerAControllerCD | FillerBControllerCD | FILL_A_DONE | String (full BottleContext¦measuredAMl) | 11005 | All A outputs safe; matching context; measured A acceptable | Implemented M4-internal idempotent hand-off
P4 start | M3 Rotary | CapperControllerCD | BOTTLE_AT_CAP | String (full BottleContext) | 11007 | Same bottleId physically confirmed at Position 4 | Implemented at M3 sender and M4 Capper receiver

## M4 V1.2 Tests
M4 V1.2 — Implementation Verification
Source: COMPSYS704_M4_GP_IP_Integration_Interface_Contract_V1_2.docx ¦ Implementation sync: 2 September 2026
M4 local implementation gates are complete: production XML is registered, deterministic model tests pass, and the two-size SystemJ demo passes. Remaining cross-member work is limited to pending M2 profile and downstream SortPack peer endpoints.
ID | Scenario | Pass condition | Owner / freeze note
T1 | Repeated status polling | No M4 operation starts, advances, resets or acknowledges. | PASS — read-only polling implemented
T2 | S¦200¦GEOM_S¦PACK_S, ratio 60/40 | 120 mL A + 80 mL B; GEOM_S set-points; PACK_S lane/package; exactly-once completion. | PASS — model test and SystemJ demo
T3 | L¦500¦GEOM_L¦PACK_L, ratio 60/40 | 300 mL A + 200 mL B; GEOM_L set-points; PACK_L lane/package; exactly-once completion. | PASS — model test and SystemJ demo
T4 | Unknown context, local ratio out of range or recipe-pair mismatch | Unknown/local-invalid input starts no actuator. M1 rejects a non-100-sum pair before dispatch; forced complement mismatch keeps Filler B closed and reports FAULT. | PASS — M1 validation and M4 fault test
T5 | FILL_A_DONE identity and gating | Filler B starts only after one matching safe completion; stale/duplicate messages do no work. | PASS — identity/gating test
T6 | Position, sensor, timeout or overflow fault | Outputs de-energise; no false FILL_A_DONE, MARK_FILLED or MARK_CAPPED. | PASS — safe-state fault tests
T7 | Capper S/L profile and duplicate event | Correct grip/clamp set-points; one guarded sequence; no duplicate restart. | PASS — S/L geometry and idempotency test
T8 | M2-to-SortPack context and placement | Unchanged full BottleContext reaches 11012; expected lane and placement are confirmed before count; BOTTLE_DONE remains M2-owned. | M4 PASS; merged M2 sender test pending
Implementation Handoff Checklist
Owner | Required action | Status | Evidence before freeze
M1 | Retain frozen ratio/status ports and M2-only BOTTLE_DONE; M1 recipe-pair validation and Conveyor/Rotary sender mappings are confirmed. | COMPLETE AT M1; M2 PEERS PENDING | Current M1 source/XML, OrderV1SelfTest and integration regression
M2 | Preserve full context for LOAD_PROFILE, UNLOAD_PROFILE and BOTTLE_READY_FOR_SORT; retain BOTTLE_DONE ownership. | PAYLOAD APPROVED; M2 IMPLEMENTATION PENDING | Implementation and integration-test evidence
M3 | Reconcile Rotary Controller with M1; approve ROTARY_BOTTLE_CONTEXT, BOTTLE_AT_FILL and BOTTLE_AT_CAP; retain Plant 12003. | COMPLETE AT M3/M4 BOUNDARY | Current M3 source/XML and interface validator
M4 | Implement Registry, Filler A/B, Capper and SortPack on assigned ports; publish target-volume and bottleId clarifications in the next contract revision; verify merged XML; execute T1-T8. | IMPLEMENTED AND VERIFIED | Member4ModelSelfTest PASSED; Member3Member4IntegrationSelfTest PASSED; two-size SystemJ demo PASSED; production XML registered
Definition of Integration Done
M4 local definition of done is satisfied: S/L bottles retain one validated context; Filler B is gated by matching safe FILL_A_DONE; faults enter a safe state; MARK_FILLED and MARK_CAPPED reach RotaryTablePlantCD:12003 without M4 claiming BOTTLE_DONE; SortPack verifies lane and placement before counting. Full group end-to-end completion still requires the pending M2 Loader/Conveyor/Labeller/Unloader and Transfer Adapter endpoints.